{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["PSP Aufbau"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"PSP Aufbau","index":0,"n_rows":22,"n_cols":14,"rows_kept":22,"cut":false,"hidden":false,"merged":[[5,5,5,11]]}
[null,"PROJEKTSTRUKTURPLAN"]
[null,"Projekttitel",null,"Parsec Iron Puffin",null,"Gruppe",null,"Gruppe 4"]
[null,"Projektleiter",null,"Levin",null,"Datum",null,"2019-05-28"]
[]
[]
[null,"PROJEKT",null,null,null,"Parsec Iron Puffin"]
[]
[]
[null,"PHASE",null,"Vorarbeiten",null,"Analyse",null,"Konzept",null,"Implementierung",null,"Qualitätsicherung",null,"Abnahme"]
[]
[]
[null,null,null,"Kick Off",null,"Mindmap erstellen",null,"ERD erstellen",null,"Implementation vom Frontend",null,"Systemtest",null,"Abnahme des Prototyps und Quellcodes"]
[]
[null,null,null,"Rollen verteilen",null,"Fragenkatalog erstellen",null,"Use-Case erstellen",null,"Implementation vom Backend",null,"Codereview",null,"Prozessorientierte Präsentation"]
[]
[null,null,null,"Ziele vereinbaren",null,"Analyse der zuverwendeten Techniken",null,"Schnittstellen definieren",null,"Datenbank aufsezten"]
[]
[null,null,null,"Kommunikationsplan erstellen",null,"Zeitplan und Projektstrukturplan erstellen",null,"Papierprototyp entwerfen",null,"CI/CD Pläne aufsetzen"]
[null,"AUFGABE"]
[{"$nulls":5},"Infrastrukturanforderung definieren",null,"Prozessorientierte Präsentation entwerfen"]
[]
[{"$nulls":5},"Pflichtenheft erstellen"]